## Sheet1
task | Assigned to | Assigned to | Assigned to | Assigned to | status | severity
Add a drop down for the universities listing all the universities | Spandana | Gopinadh |  |  | completed | high
Add a functionality where you can add a new university into the existing list | Sindhuja | Nihitha | Spandana |  | completed | high
Add validations for all the input fields | Srichaitanya | Lokesh |  |  | In progress | high
Make the phone number mandatory | Abishai |  |  |  | completed | high
Add a functionality to validate the entered phone number belongs to the same user | Abishai | Srichaitanya | Nihitha | Lokesh | yet to start | high
Provide an option to undelete a fraternity even after the fraternity is deleted | Sindhuja | Nihitha |  |  | completed | medium
Populate the subscription period and status of the fraternity ( i.e., suspend/ active/ etc..) | Spandana | Gopinadh |  |  | completed | medium
Provide a suspend button- a fraternity is newly added by admin but the payment is not done or the subscription period is passed behind, then the status of that fraternity should be in suspend | Sindhuja | Nihitha |  |  | completed | medium
In the events page, use a date picker to select the date | Spandana | Sindhuja |  |  | completed | medium
Automatically send notifications to the fraternities when there is a need for the payment or regarding the expiration of the subscription period | Abishai | Srichaitanya |  |  | yet to start | high
Add a default image for the fraternities if no image is provided at the start | Lokesh | Gopinadh |  |  | yet to start | medium
Check the focusing of all the input fields ( mainly “university” in admin page and “email” in home page) | Sindhuja | Nihitha | Spandana |  | completed | high
Re-check the email functionality | Abishai |  |  |  | In progress | high
whenever a fraternity is added to the existing partyguard list, send an email having a link to the fraternity first time login page with populated subscription code etc. – this confirms that the validation of the fraternity is done through email | Lokesh | Srichaitanya | Gopinadh |  | yet to start | low
Provide host with “change the password “ option | Sindhuja | Spandana |  |  | In progress | high
If there is any change in email of the fraternity, then notify the change to the old email and confirm before further processing | Abishai | Nihitha | Srichaitanya |  | yet to start | high
Confirm with the client that what does a quote contain and how is the price negotiated? | Nihitha |  |  |  | completed | high
Store the prices in database | Sindhuja |  |  |  | yet to start | high
Event: add a date picker | Spandana | Sindhuja |  |  | completed | medium
Event: Add a start date | Spandana | Sindhuja |  |  |  | medium
Change the radio button functionality in the members page of host | Abishai | Nihitha |  |  | completed | high
Admin side, add customer page: On clicking “Save”, show some confirmation | Srichaitanya | Lokesh | Gopinadh |  | yet to start | medium
Manage the guards | Srichaitanya | Lokesh |  |  | In progress | high
Phone number verification of the guards | Abishai | Srichaitanya | Nihitha | Sindhuja | yet to start | high
Before start of the project, send a prior message to the guards and ask for a reply which in turn confirms that the guard is ready to take the alerts | Lokesh | Sindhuja | Spandana |  | yet to start | low
Host adds the guard (registration of the guard by himself may not be needed) | Abishai | Nihitha | Spandana | Lokesh | yet to start | low